## Slide 1
AN IMPLEMENTATION GUIDE
WRAP
Wellness Recovery
Action Plan
Implementing WRAP in a Low Barrier Shelter Medical Respite Program
A practical guide for clinical staff and program leadership
Trauma-informed • Person-centered • Recovery-oriented
Notes: Welcome participants. Frame the session: WRAP is an evidence-based, peer-led wellness self-management process. Medical respite is short-term post-acute care for people experiencing homelessness. This training shows how to braid the two together inside a low-barrier shelter environment. Audience is mixed clinical staff and leadership; we'll move from concepts to concrete implementation steps.

## Slide 2
Implementing WRAP in Low Barrier Shelter Medical Respite
2
WHAT WE'LL COVER
Training Agenda
01
Foundations
WRAP, medical respite, and low-barrier shelter
02
The Fit
Why WRAP works for this population
03
Implementation
Steps from buy-in to first group
04
Operations
Staffing, scheduling, documentation
05
Outcomes
Metrics, barriers, and funding
Notes: Walk through the five sections. Note that the first half builds shared vocabulary across staff and leadership; the second half is operational. Encourage participants to flag questions specific to their role as we go.

## Slide 3
Implementing WRAP in Low Barrier Shelter Medical Respite
3
FOUNDATIONS
What is WRAP?
A simple, structured, peer-led self-management process developed in 1997 by Mary Ellen Copeland and a group of people with lived mental health experience. SAMHSA-listed evidence-based practice.
Wellness Toolbox
Simple, safe, free tools a person uses to stay well
Daily Maintenance
What I do every day to feel my best
Triggers
External events that may set off symptoms — and the response plan
Early Warning Signs
Internal subtle shifts and how I'll act on them
When Things Break Down
Steps to take when symptoms worsen
Crisis & Post-Crisis
How others should support me — and the path back
Notes: WRAP is non-clinical, self-directed, and peer-led. The wellness toolbox is the foundation — everything else uses the tools. Each part is written by the participant in their own words. Emphasize: the participant owns their plan; staff do not write it for them. Evidence base: Cook et al. RCTs (Schizophrenia Bulletin 2011; Psychiatric Services 2012) showed reduced symptoms, increased hope, improved QOL.

## Slide 4
Implementing WRAP in Low Barrier Shelter Medical Respite
4
FOUNDATIONS
The Five Key Concepts
1
Hope
Belief that we can get well, stay well, and move toward our goals.
2
Personal Responsibility
Each of us decides what to do to stay well.
3
Education
Learning about what we experience to make informed choices.
4
Self-Advocacy
Reaching out, naming what we need, asking for it directly.
5
Support
Giving and receiving help — on our own terms.
Notes: These five concepts are the values frame around every WRAP group. They map almost perfectly onto trauma-informed care principles and onto low-barrier philosophy: autonomy, choice, voice, and dignity. Use these concepts to brief medical and shelter staff so they reinforce — not undermine — what participants are learning.

## Slide 5
Implementing WRAP in Low Barrier Shelter Medical Respite
5
FOUNDATIONS
Where We're Working
Low Barrier Shelter
No ID, sobriety, or treatment requirements at entry
Flexible curfews; 3–5 missed nights before discharge
Harm reduction approach; meets people where they are
Housing First values: autonomy, choice, dignity
Discharge used only as a last resort
Medical Respite Program
Short-term post-acute care for people experiencing homelessness
Too ill for street or shelter, not ill enough for hospital
NHCHC Standards (2021/2025): 8 core program standards
Wraparound services + care coordination during stay
152+ programs across 40 states (NIMRC, 2023)
Notes: Frame the operating environment. Low-barrier shelter removes the entry hurdles traditional shelters impose — sobriety, ID, curfews. Medical respite adds a clinical layer for post-acute recovery. When co-located, the respite program inherits low-barrier values: harm reduction, voluntary engagement, no coercion. Sources: HHRC Low-Barrier Shelter Policies (Oct 2025); NHCHC Standards for Medical Respite Care Programs (2021/2025); ASPE Issue Brief Dec 2024.

## Slide 6
Implementing WRAP in Low Barrier Shelter Medical Respite
6
THE FIT
Why WRAP Belongs Here
High behavioral health burden
Co-occurring mental health and SUD are the norm, not the exception, among medical respite guests.
Trauma is pervasive
Trauma precedes homelessness, results from it, and is reinforced by hospitalization itself.
A safe pause
Respite offers a rare stable window — bed, food, safety — to build a wellness plan that lasts beyond the stay.
Aligned values
WRAP's hope, choice, self-advocacy mirror low-barrier and Housing First principles.
Peer-led works
Cook et al. RCT (n=519) showed reduced symptoms, greater hope, improved QOL at 6-month follow-up.
Notes: Make the case for fit. People entering medical respite often have complex trauma plus behavioral health needs (Kushel et al.; Wadhera et al.). WRAP gives them an evidence-based, non-clinical, dignity-preserving tool — and the respite stay creates the calm, repeatable conditions a person needs to actually build their plan. The Cook RCTs are the strongest evidence base; cite them when talking to funders.

## Slide 7
Implementing WRAP in Low Barrier Shelter Medical Respite
7
IMPLEMENTATION
A Six-Phase Roadmap
1
Buy-in
Leadership, clinical, peers, guests
2
Train
Send 2+ staff to Seminar I, II, III
3
Adapt
Tailor format to respite reality
4
Pilot
First cohort, small group or 1:1
5
Embed
Care plans, documentation, handoff
6
Sustain
Fidelity, funding, peer pipeline
Expect 4–6 months from buy-in to first cohort; longer if hiring peer staff.
Notes: Walk left to right. Most programs underestimate phase 1 (buy-in) and phase 5 (embedding into care plans). Encourage participants to identify a single executive sponsor and a single clinical champion before phase 2. Timeline assumes you can backfill staff to attend Seminars; if not, plan longer.

## Slide 8
Implementing WRAP in Low Barrier Shelter Medical Respite
8
PHASE 1
Building Stakeholder Buy-In
Leadership
Frame WRAP as outcomes lever: ED diversion, engagement, readmission risk reduction.
Clinical staff
Show how WRAP complements — does not replace — clinical care plans.
Peers / lived experience
Center this group early; they are the future facilitators.
Guests
Invite guest input through listening sessions before launch.
Notes: Buy-in is iterative, not one meeting. Bring data to leadership (ED utilization baselines, length of stay), bring testimonials and the workflow to clinical staff, and bring co-design seats to peers and guests. If you skip the guest voice, you will design a program guests won't attend.

## Slide 9
Implementing WRAP in Low Barrier Shelter Medical Respite
9
PHASE 2
Facilitator Training Pathway
All training is credentialed through the Copeland Center / Advocates for Human Potential (AHP).
Seminar I
Personal WRAP
Four 4.5-hour sessions • $399 + materials • No prerequisites
Seminar II
Certified Facilitator
Three to five 8-hour sessions • $1,099 • Requires Seminar I
Seminar III
Advanced Level Facilitator (ALF)
Highest credential • Can train and certify other facilitators
Recertification
Ongoing fidelity
Required to keep facilitator and ALF credentials active
Target: at least two trained facilitators on staff so groups continue through PTO and turnover.
Notes: Seminar pricing is current as of WRAP, Inc. published rates. Budget travel and backfill in addition to tuition. Best practice: hire or develop at least one peer specialist who can become an ALF. ALFs are the only people who can certify new facilitators, so an in-house ALF is the long-game move for sustainability.

## Slide 10
Implementing WRAP in Low Barrier Shelter Medical Respite
10
PHASE 3
Adapt the Format to Respite Reality
Open Group
Drop-in welcome
Fits short, variable stays
Plus: low commitment
Minus: less continuity
Closed Cohort
Fixed 8-week group
Mirrors RCT fidelity
Plus: stronger bonds
Minus: requires longer stay
1:1 Sessions
Paired with peer
Bedside-accessible
Plus: meets medical needs
Minus: staff intensive
Most respite programs land on a hybrid: open weekly group + 1:1 bedside check-ins.
Notes: Average medical respite stay is 30–60 days — too short for a strict 8-week closed cohort with full fidelity. Hybrid format protects engagement without sacrificing the WRAP elements. The closed cohort can still happen for long-stay guests or for post-discharge alumni who return weekly.

## Slide 11
Implementing WRAP in Low Barrier Shelter Medical Respite
11
PHASE 3
Trauma-Informed & Harm Reduction
SAMHSA's six trauma-informed principles map directly onto WRAP's structure and onto low-barrier policy. Your job during adaptation is to keep all three aligned.
Safety
Trustworthiness & Transparency
Peer Support
Collaboration & Mutuality
Empowerment, Voice & Choice
Cultural, Historical & Gender Issues
Harm reduction is not a separate track — it is how every WRAP conversation handles substance use: no abstinence prerequisite, no coercion, focused on reducing harm and increasing safety.
Notes: Source: SAMHSA Trauma-Informed Approaches; NACCHO Harm Reduction as a Trauma-Informed Approach. Reinforce that resisting re-traumatization in the respite environment requires consistency: front-desk staff, nurses, and peer facilitators must all use the same language. Train everyone — not just the WRAP team.

## Slide 12
Implementing WRAP in Low Barrier Shelter Medical Respite
12
STAFFING
Peer Support is the Engine
Who facilitates
Certified WRAP Facilitator credential required
Peer specialist with lived experience preferred
Co-facilitation with clinical staff supports fidelity
Compensated, supervised, and on the org chart
True cost of a peer role
Salary + benefits (often underbudgeted)
Reflective supervision by trained supervisor
Ongoing training and certification renewals
Tech, workspace, and transportation support
Notes: Peer support is a key vehicle for SAMHSA's trauma-informed approach and the engine of WRAP fidelity (intervention was peer-led in the Cook RCTs). Common mistake: funding only the salary line. Use the RecoveryPeople 'Peer Program Cost Awareness' worksheet to build a real budget including supervision, training, tech, and admin support.

## Slide 13
Implementing WRAP in Low Barrier Shelter Medical Respite
13
PHASE 5
Documentation & Care Plan Integration
DO
Note WRAP participation, not WRAP content
Link WRAP wellness goals to the respite care plan
Add a WRAP handoff section in discharge summaries
Send WRAP summary (with consent) to PCP / CCBHC
DON'T
Don't copy a participant's plan into the EHR
Don't share crisis plan details without consent
Don't use WRAP language to justify discharge
Don't make WRAP a condition of bed retention
Notes: The biggest implementation pitfall is over-clinicalizing WRAP. WRAP is participant-owned. Staff document attendance and themes, never copy plan contents. Build a single-page consented summary that the participant chooses to share with PCP or CCBHC at discharge — that's where the value compounds across the care continuum.

## Slide 14
Implementing WRAP in Low Barrier Shelter Medical Respite
14
OUTCOMES
What to Measure
Engagement
% of respite guests offered WRAP
% who attend ≥1 session
Completion rates
Self-report
Hope Scale
Recovery Assessment Scale (RAS)
WHO QOL-BREF
Health utilization
ED visits at 90/180 days
30-day readmissions
PCP linkage rate
Housing & continuity
Discharge destination
Housing placement at 90 days
Return to respite rate
Baseline first; review quarterly with peer facilitators and guests at the table.
Notes: Pick a small bundle — three to four metrics — and stick with them. The Cook RCTs validate hope, RAS, and symptom inventories as legitimate self-report measures. Pair self-report with claims/encounter data (ED, readmits) for funders. ASPE flagged that respite programs often fail to track housing status post-discharge — design for that from day one.

## Slide 15
Implementing WRAP in Low Barrier Shelter Medical Respite
15
REAL TALK
Common Barriers — and What Works
Short, variable stays
Hybrid format; bedside 1:1; alumni group
Acute symptoms / withdrawal
Defer participation; harm-reduction posture; revisit
Staff skepticism (WRAP ≠ clinical)
Co-facilitation; include staff in Seminar I
Facilitator turnover
Train 2+; build internal ALF; peer pipeline
Funding uncertainty
Braid: Medicaid CCBHC + HRSA BHSE + county
Cultural and language gaps
Hire to community; adapted materials; translation
Notes: Be candid with leadership: these barriers are universal. The most common fatal error is funding a single peer facilitator with no backup — that program collapses on first turnover. Build redundancy from day one. Use this slide as a discussion prompt with the room.

## Slide 16
Implementing WRAP in Low Barrier Shelter Medical Respite
16
SUSTAINING THE WORK
Funding the Program
Medicaid CCBHC
Prospective payment for behavioral health; now a permanent state plan option (CAA 2024).
Medicaid §1115
Health-related social needs coverage in select states; can include respite + post-respite.
SAMHSA CCBHC-E
Up to $1M/yr for 4 years — planning, development, improvement & advancement.
HRSA BHSE
Behavioral Health Service Expansion grants for HCH-designated health centers.
State / county BH
Local behavioral health authority contracts; AOT and crisis service dollars.
Philanthropy
United Way, hospital community benefit, recovery-focused foundations.
Notes: Most sustainable programs braid at least three streams. CCBHC is the strongest long-term anchor in states that have adopted it; check your state's status before assuming availability. HRSA BHSE is only available to existing HCH grant recipients. Hospital community benefit dollars are an underused source — frame WRAP as readmission reduction.

## Slide 17
17
CASE STUDY
A Comparable Program in Practice
Program profile
Setting
Urban low-barrier shelter co-located with 30-bed medical respite unit
Guests served
~350 admissions / year; avg. stay 42 days; 70% with behavioral health dx
WRAP format
Hybrid: open weekly group + bedside 1:1 with peer specialist
Staffing
2 Certified WRAP Facilitators (1 peer, 1 RN co-facilitator); 1 in-house ALF
Funding braid
Medicaid CCBHC + HRSA BHSE + county behavioral health contract
12-month outcomes
62%
of eligible guests engaged ≥ 1 WRAP session
38%
drop in ED visits at 90 days post-discharge
+24%
improvement on Hope Scale (matches Cook RCT magnitude)
Lessons learned
Bedside 1:1 reached guests too unwell to leave their bed for groups
Co-facilitation with a nurse softened clinical staff skepticism
Alumni group post-discharge sustained engagement past respite
Illustrative composite based on published medical respite outcomes and Cook et al. RCT effect sizes.
Notes: Use this slide as a discussion anchor — it's an illustrative composite, not a single named site, drawing on publicly reported medical respite characteristics (NHCHC / NIMRC) and the peer-led WRAP outcomes documented in the Cook et al. RCTs. Tell the room: these are realistic targets for a respite program of this size. Encourage attendees to map their own program against the profile fields on the left and identify which gaps to close first.

## Slide 18
Implementing WRAP in Low Barrier Shelter Medical Respite
18
WHAT TO DO MONDAY
Your First 90 Days
Days 1–30
Name an exec sponsor & clinical champion
Hold listening sessions with guests & peers
Map current behavioral health workflows
Baseline ED, readmit, housing metrics
Days 31–60
Register staff for Seminar I
Draft workflow + documentation policy
Identify funding braid
Choose pilot format (open / cohort / 1:1)
Days 61–90
Run staff & guest orientation
Launch pilot cohort
Track engagement weekly
Schedule 6-month fidelity check
Notes: This is the slide leadership will remember. Encourage them to leave the session with a named sponsor, a named champion, and a 30-day meeting on the calendar. Implementation drifts when no one owns it past the kickoff.

## Slide 19
Implementing WRAP in Low Barrier Shelter Medical Respite
19
RESOURCES
Where to Go Next
Hope. Personal responsibility. Education. Self-advocacy. Support.
WRAP & training
wellnessrecoveryactionplan.com • copelandcenter.com • ahpnet.com
Medical respite standards
nhchc.org • nimrc.org (Standards 2021/2025; Clinical Guidelines 2023)
Trauma-informed & harm reduction
samhsa.gov • naccho.org
Evidence base
Cook et al., Schizophr Bull 2011 & Psychiatr Serv 2012 (RCT, n=519)
Funding
medicaid.gov (CCBHC) • samhsa.gov/ccbhc-e • bphc.hrsa.gov
Thank you • Questions?
Notes: Close by inviting questions and a one-thing commitment from each participant: 'what's one action you'll take in the next two weeks?' Capture commitments and follow up at 30 days. References slide is intended as a take-away — share digitally with participants after the session.